## Gantt Overview
|  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4
ID | Task | Duration | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 9 | Week 10 | Week 11 | Week 12
| Experiment | 90 days
1.0 | 1. Single Stock Data (Data Acquisition) | 10 days | bar: Month 1 Week 1 to Month 1 Week 2
2.0 | 2. Sharpe Ratio (Feature Engineering) | 10 days | bar: Month 1 Week 2 to Month 1 Week 3
3.0 | 3. Portfolio Selection | 10 days | bar: Month 1 Week 4 to Month 2 Week 5
4.0 | 4. Time-Series Prediction | 20 days | bar: Month 2 Week 6 to Month 3 Week 9
5.0 | 5. Portfolio Optimization | 20 days | bar: Month 3 Week 9 to Month 3 Week 12
6.0 | 6. Evaluate Solution (Model Selection) | 20 days | bar: Month 3 Week 12 to Month 4 Week 11
| Write-Up | 20 days | bar: Month 4 Week 9 to Month 4 Week 12

## L-1
a.
Experiment
1.0 | 2.0 | 3.0 |  | 4.0 | 5.0 | 6.0
1. Single Stock Data (Data Acquisition) | 2. Sharpe Ratio (Feature Engineering) | 3. Portfolio Selection |  | 4. Time-Series Prediction | 5. Portfolio Optimization | 6. Evaluate Solution (Model Selection) | b.
Write-Up
1. Single Stock Data (Data Acquisition) | 2. Sharpe Ratio (Feature Engineering) | 3. Portfolio Selection |  | 4. Time-Series Prediction | 5. Portfolio Optimization | 6. Evaluate Solution (Model Selection) | Write-Up
1.1 Setup environment | 2.1 Compute returns: Daily, Weekly, Monthly | 3.1 Setup portfolio constraints: Mean-Variance, Budget |  | 4.1 Review prediction methods and techniques. Understand parameter setting and limitation. | 5.1 Set optimization problem: objective function, decision variables, constraints | 6.1 Define baseline performance (historical indices) | Problem Statement
1.2 Identify source and collect data | 2.2 Compute variance of returns: Daily, Monthly, Weekly | 3.2 Setup objective function: minimize Variance |  | 4.1.1 ARIMA | 5.2 Review optimization method/technique | 6.2 Compare against real data | Background
1.2.1 List of stocks | 2.3 Scale risk-free rate of return to match asset retuns frequenct: Check distribution | 3.3 Produce portfolio weights |  | 4.1.2 LSTM | 5.2.1 Analytic solution | 6.3 Evaluate significance of result, apply student t-test | Literature Review
1.2.2 Each stock historical prices | 2.4 Compute Sharpe Ratio | 3.3.1 Two-security case |  | 4.1.3 Linear Model Regression | 5.2.2 Linear programming |  | Method
1.2.3 List of indices |  | 3.3.2 Three-security case |  | 4.1.4 Neural Network Regression | 5.2.3 Quadratic programming |  | Proposed Work
1.2.4 Indices historical series |  | 3.3.3 Four-security case |  | 4.1.5 Support Vector Regression | 5.2.4 Non-linear programming |  | Bibliography
1.2.5 Risk-free rate series |  | 3.3.4 Five-security case |  | 4.2 Select target for prediction: value type, time-horizon | 5.2.5 Cone programming / Convex optimization |  | Result Data
1.3 Check data / basic statistics |  | 3.3.5 Ten-security case |  | 4.3 Select dependent variable for prediction | 5.2.6 Genetic Algoirthm |  | Result Analysis
1.4 Resampling to study frequency: Daily, Weekly, Monthly |  | 3.4 Plot E-V for all candidate portfolios |  | 4.4 Choose performance measures | 5.3 Apply optimization method to portfolio optimization problem |  | Evaluation
1.5 Check normality (Chi-square, Pearson) |  | 3.5 Plot Efficient-Frontier curve and determine efficient set |  | 4.5 Choose algorithms | 5.3.1 Greedy / Genetic Algorithm |  | Abstract
1.6 Store data for use |  | 3.6 Use Sharpe ratio as rule to create portfolio |  | 4.5.1 ARIMA | 5.3.2 Quadratic Programming Solver |  | Discussion
|  |  |  | 4.5.2 LSTM | 5.3.3 Convex Optimization Solver |  | Future Work
|  |  |  | 4.5.3 Linear Model (Least Square Regression) | 5.4 Validate / compare solutions |  | End
4.5.4 Neural Network Regression
4.5.5 Support Vector Regression
4.6 Acquire/prepare data for prediction
4.7 Partition data to traning set and testing set
4.8 Select the best model parameters for future predictions
4.9 Calculate performance measure
4.10 Evaluate significance of the results, apply statistical tests such as t-test

## L-2
[6 empty] | a. |  |  |  | b. |  |  |  |  | Experiment
[7 empty] | Experiment |  |  | Write-Up |  |  |  |  | 1. Single Stock Data (Data Acquisition)
1.1 Setup environment
1.2 Identify source and collect data
1.2.1 List of stocks
1.2.2 Each stock historical prices
1.2.3 List of indices
1.2.4 Indices historical series
1.2.5 Risk-free rate series
1.3 Check data / basic statistics
1.0 |  |  | 2.0 |  | 3.0 |  |  | 4.0 |  |  | 5.0 |  | 6.0 |  | 1.4 Resampling to study frequency: Daily, Weekly, Monthly
1. Single Stock Data (Data Acquisition) |  |  | 2. Sharpe Ratio (Feature Engineering) |  | 3. Portfolio Selection |  |  | 4. Time-Series Prediction |  |  | 5. Portfolio Optimization |  | 6. Evaluate Solution (Model Selection) |  | 1.5 Check normality (Chi-square, Pearson)
1.6 Store data for use
2. Sharpe Ratio (Feature Engineering)
2.1 Compute returns: Daily, Weekly, Monthly
2.2 Compute variance of returns: Daily, Monthly, Weekly
2.3 Scale risk-free rate of return to match asset retuns frequenct: Check distribution
|  | 1.1 |  | 2.1 |  |  | 3.1 |  | 4.1 |  |  | 5.1 |  | 6.1 | 2.4 Compute Sharpe Ratio
|  | 1.1 Setup environment |  | 2.1 Compute returns: Daily, Weekly, Monthly |  |  | 3.1 Setup portfolio constraints: Mean-Variance, Budget |  | 4.1 Review prediction methods and techniques. Understand parameter setting and limitation. |  |  | 5.1 Set optimization problem: objective function, decision variables, constraints |  | 6.1 Define baseline performance (historical indices) | 3. Portfolio Selection
3.1 Setup portfolio constraints: Mean-Variance, Budget
3.2 Setup objective function: minimize Variance
3.3 Produce portfolio weights
3.3.1 Two-security case
3.3.2 Three-security case
|  | 1.2 |  | 2.2 |  |  | 3.2 |  | 4.2 |  |  | 5.2 |  | 6.2 | 3.3.3 Four-security case
|  | 1.2 Identify source and collect data |  | 2.2 Compute variance of returns: Daily, Monthly, Weekly |  |  | 3.2 Setup objective function: minimize Variance |  | 4.2 Select target for prediction: value type, time-horizon |  |  | 5.2 Review optimization method/technique |  | 6.2 Compare against real data | 3.3.4 Five-security case
3.3.5 Ten-security case
3.4 Plot E-V for all candidate portfolios
3.5 Plot Efficient-Frontier curve and determine efficient set
3.6 Use Sharpe ratio as rule to create portfolio
4. Time-Series Prediction
|  | 1.3 |  | 2.3 |  |  | 3.3 |  | 4.3 |  |  | 5.3 |  | 6.3 | 4.1 Review prediction methods and techniques. Understand parameter setting and limitation.
|  | 1.3 Check data / basic statistics |  | 2.3 Scale risk-free rate of return to match asset retuns frequenct: Check distribution |  |  | 3.3 Produce portfolio weights |  | 4.3 Select dependent variable for prediction |  |  | 5.3 Apply optimization method to portfolio optimization problem |  | 6.3 Evaluate significance of result, apply student t-test | 4.1.1 ARIMA
4.1.2 LSTM
4.1.3 Linear Model Regression
4.1.4 Neural Network Regression
4.1.5 Support Vector Regression
4.2 Select target for prediction: value type, time-horizon
| ˀ | 1.4 |  | 2.4 |  |  | 3.4 |  | 4.4 |  |  | 5.4 |  |  | 4.3 Select dependent variable for prediction
|  | 1.4 Resampling to study frequency: Daily, Weekly, Monthly |  | 2.4 Compute Sharpe Ratio |  |  | 3.4 Plot E-V for all candidate portfolios |  | 4.4 Choose performance measures |  |  | 5.4 Validate / compare solutions |  |  | 4.4 Choose performance measures
4.5 Choose algorithms
4.5.1 ARIMA
4.5.2 LSTM
4.5.3 Linear Model (Least Square Regression)
4.5.4 Neural Network Regression
|  | 1.5 |  |  |  |  | 3.5 |  | 4.5 | [5 empty] | 4.5.5 Support Vector Regression
|  | 1.5 Check normality (Chi-square, Pearson) |  |  |  |  | 3.5 Plot Efficient-Frontier curve and determine efficient set |  | 4.5 Choose algorithms | [5 empty] | 4.6 Acquire/prepare data for prediction
4.7 Partition data to traning set and testing set
4.8 Select the best model parameters for future predictions
4.9 Calculate performance measure
4.10 Evaluate significance of the results, apply statistical tests such as t-test
5. Portfolio Optimization
|  | 1.6 |  |  |  |  | 3.6 |  | 4.6 | [5 empty] | 5.1 Set optimization problem: objective function, decision variables, constraints
|  | 1.6 Store data for use |  |  |  |  | 3.6 Use Sharpe ratio as rule to create portfolio |  | 4.6 Acquire/prepare data for prediction | [5 empty] | 5.2 Review optimization method/technique
5.2.1 Analytic solution
5.2.2 Linear programming
5.2.3 Quadratic programming
5.2.4 Non-linear programming
5.2.5 Cone programming / Convex optimization
[9 empty] | 4.7 | [5 empty] | 5.2.6 Genetic Algoirthm
[9 empty] | 4.7 Partition data to traning set and testing set | [5 empty] | 5.3 Apply optimization method to portfolio optimization problem
5.3.1 Greedy / Genetic Algorithm
5.3.2 Quadratic Programming Solver
5.3.3 Convex Optimization Solver
5.4 Validate / compare solutions
6. Evaluate Solution (Model Selection)
[9 empty] | 4.8 | [5 empty] | 6.1 Define baseline performance (historical indices)
[9 empty] | 4.8 Select the best model parameters for future predictions | [5 empty] | 6.2 Compare against real data
6.3 Evaluate significance of result, apply student t-test
Write-Up
Problem Statement
Background
Literature Review
[9 empty] | 4.9 | [5 empty] | Method
[9 empty] | 4.9 Calculate performance measure | [5 empty] | Proposed Work
Bibliography
Result Data
Result Analysis
Evaluation
Abstract
[9 empty] | 4.10 | [5 empty] | Discussion
[9 empty] | 4.10 Evaluate significance of the results, apply statistical tests such as t-test | [5 empty] | Future Work
End